Volunteering Development Strategy in the Republic of Slovenia until 2030

Table of contents

1.	Introduction	3

2.	Purpose of the Strategy	5

3.	Needs analysis of volunteer organisations/volunteering	5

4.	Fundamental policies for the development of volunteering	6

5.	Strategic development objectives of volunteer organisations/volunteering	6

6.	The role of the state and self-governing local communities in achieving development  objectives	7

7.	Main fields of volunteering development	8

8.	Action plan for the implementation of the Volunteering Development Strategy	9

9.    Conclusion	20

10.   References	20

List of abbreviations

BEV2030 – Blueprint for European Volunteering 2030

BI – budget item

CEV – Centre for European Volunteering

ICT – information and communication technology

NGO – Non-Governmental Organisation

OEDC – Organisation for Economic Co-operation and Development

P.A.V.E. – Policy Agenda for Volunteering in Europe

ZNOrg – Zakon o nevladnih organizacijah – Non-Governmental Organisations Act

ZProst – Zakon o prostovoljstvu – Volunteering Act

ZZUKDPSS – Zakon o začasnih ukrepih za izboljšanje kadrovskih in delovnih pogojev ter zmogljivosti pri izvajalcih socialnovarstvenih storitev in dolgotrajne oskrbe – Act on Temporary Measures to Improve Personnel and Working Conditions and  Capacity of Providers of Social Protection and Long-Term Care Services

- Introduction

The Strategy was drafted on the basis of Article 36 of the Volunteering Act (ZProst), which stipulates the Government of the Republic of Slovenia’s commitment to adopting a development document (i.e. an ordinance) to promote the systematic and long-term development of volunteering Slovenia. This document will set out a five-year volunteering development strategy and define core policies and measures to promote volunteering. It will also set out joint measures for the promotion and development of volunteering as well as defining special measures to be adopted in individual fields of public regulation and state action to enable the development of volunteering in Slovenia. Alongside this, the Strategy for the Development of Non-Governmental Organisations in the Republic of Slovenia until 2030 was also being prepared.

The Strategy is a continuation of the Strategy for Developing Non-Governmental Organisations and Volunteering until 2023 in the section that regulates the field of volunteering. It defines strategic areas based on key elements for the existence and development of volunteering and volunteer organisations in Slovenia. Non-governmental organisations are closely linked to volunteering, having developed from long-standing traditions of philanthropy and self-help common to all societies, which are based on the ethical principle of helping those beyond one’s immediate family.

Volunteering is an unpaid, socially beneficial activity in which individuals contribute their work, knowledge and experience to improve the quality of life of individuals and social groups, and to develop a society based on solidarity, humanity and equality. Volunteering strengthens solidarity among people, encourages human capacity development and lifelong learning, and ensures social cohesion and cooperation in addressing the problems of individuals and society. However, volunteering is often overlooked in public policies, which is why the OECD calls for better measurement, evaluation and inclusion of volunteering in policy-making, particularly in healthcare, education, the environment and social assistance. An OECD study entitled Unleashing the Potential of Volunteering for Local Development suggests that a more structured and inclusive support system is necessary to exploit the full potential of volunteering. This includes investment in training and creating a supportive environment for volunteering.

The Volunteering Development Strategy in the Republic of Slovenia until 2030 is also based on European guidelines that established important foundations for the development of volunteering. In 2011, as part of the European Year of Volunteering, the Policy Agenda for Volunteering in Europe (P.A.V.E.) was drafted. This was the first strategic framework at European level to promote volunteering and create a supportive environment. These foundations were further upgraded by the Blueprint for European Volunteering 2030 (BEV2030), adopted in 2020 by the Centre for European Volunteering (CEV). It consists of a vision, guidelines, and recommendations for the development of volunteering over the next decade. The Strategy reflects the key recommendations of these documents, highlighting the need for a stable and sustainable environment for volunteer organisations, quality management of volunteers, greater acknowledgement of the social value of volunteering, independent and inclusive cooperation, improved opportunities for volunteering, the provision of resources, and support for quality volunteering. It also promotes improved harmonisation between stakeholders, raising awareness and cross-sectoral cooperation, all of which comply with the broader European vision of a sustainable supportive environment for volunteering. Volunteering signifies a shift from an individualistic to a more collectivist approach to society, often serving as an entry point to social activism. It is a central value of modern society as it contributes significantly to strengthening social cohesion and solidarity, promotes active citizenship and supports sustainable community development. Volunteering has a long-standing and rich tradition in Slovenia, making a notable impact on numerous areas of social life for many years. The Slovenian Development Strategy 2030 also recognises the importance of volunteering as an essential element in achieving a decent life for all.

Through their dedication, solidarity and altruistic work, volunteers contribute significantly to the development and welfare of society in numerous fields, including civil protection and rescue, the protection of human rights and civil liberties, nature conservation and environmental protection, and the creation of rich cultural and artistic events. They actively participate in social activities, promote healthy lifestyle through exercise and sport, contribute to the development of sustainable tourism, enrich educational processes, enhance community health and strengthen fundamental values such as respect for people, nature and social solidarity.

The Strategy acknowledges the important role of volunteers and volunteer organisations in addressing social needs, enhancing societal resilience and improving quality of life. Within this framework, the Strategy highlights two key points: volunteering as an independent and important social value and the vital role of volunteers and volunteer organisations in responding efficiently to current social challenges such as loneliness, mental health problems, an ageing population, armed conflicts, climate change and natural disasters.

In recent years, during which Slovenia experienced several crisis situations ranging from devastating floods and fires to the epidemic, other natural disasters and social challenges, volunteering yet again proved to be an indispensable foundation of solidarity and community interconnectedness. Volunteers, who selflessly help in the most difficult of times, contribute greatly to the welfare and resilience of society, while strengthening the sense of belonging, mutual assistance and compassion. Their actions reflect the strength of a community that can come together when it matters the most.

In accordance with Article 41 of the ZProst, the Ministry of Public Administration regularly compiles and publishes a joint annual report on volunteering in Slovenia. Statistical data for 2024 shows that 2,675 volunteer organisations and organisations providing volunteer programmes submitted their reports on volunteering. A total of 203,786 volunteers are registered with these organisations, and they performed a total of 8,560,250 volunteer hours. However, the report does not include informal volunteering, which involves activities without mediators between those in need of help and those who provide it.

The Strategy was developed in an inclusive and transparent manner in cooperation with representatives of ministries, non-governmental organisations (NGOs), volunteer organisations, the Council of the Government of the Republic of Slovenia for the Promotion of the Development of Volunteering and Volunteer and Non-Governmental Organisations, the academic community, the private sector and the wider public. The final version of the Strategy incorporates recommendations and proposals gathered during public consultations and thematic workshops, further enhancing its substantive integrity and legitimacy. The Strategy’s design enables flexible and effective responses to current social challenges. It analyses the results already attained and provides scope for the further developing and enhancing volunteering in Slovenia.

Regarding the monitoring of the Strategy’s implementation, the legislation requires the Ministry of Public Administration to submit a report to the Government within six months after the end of each two-year period. The report must include an assessment of the results and the Council’s opinion. Ministry of Public Administration shall also prepare an analysis of the fund’s spending efficiency within nine months after the adoption. Based on this analysis, the Ministry will propose changes to ensure efficient use of the fund and review the purpose of its spending, with particular emphasis on allocating a portion of the funds to operational or programmatic activities of volunteer organisations.

- Purpose of the Strategy

The general purpose of the Strategy is to support the development of organised volunteering within volunteer organisations and those providing volunteer programmes, with the aim of improving people’s living conditions, enhancing respect for human rights and promoting sustainable development in society. Promoting organised, quality volunteering enables the state to better address the challenges of our time.

Volunteers have a positive impact on the entire community because their work generates a sense of belonging. Volunteering encourages people to work together to achieve shared goals and values. It enables young people to explore their interests and forge social connections, while also having a positive impact on society. Furthermore, volunteering strengthens empathy, social responsibility and civic awareness, contributing to a better understanding of society’s needs and challenges. It enhances people’s resilience by improving mental health, fostering a sense of belonging, and developing a sense of purpose, thus enabling them to face life’s challenges. Volunteering contributes to societal resilience by promoting cooperation, solidarity and joint action during times of crisis, leading to stronger, more connected communities. Organisations that incorporate volunteers enhance their own resilience by  expanding their capacities, improving their adaptability and building the foundations for sustainable and flexible action in changing circumstances.

The Strategy aims to establish a sustainable and stable supportive environment for volunteering. This will enable volunteer organisations and volunteers to contribute successfully to social welfare. The Strategy also aims to enhance cooperation between the state, self-governing local communities and volunteer organisations, as well as promoting, advancing, and supporting volunteering while observing strategic objectives and feasible measures.

- Needs analysis of volunteer organisations/volunteering

The needs can be summarised as follows:

- Financial stability: Volunteer organisations require a stable and sustainable financial environment, as well as support for long-term planning and programme implementation. Insufficient and unstable (public) financial resources are a common issue that makes continuous planning and operations challenging. Many volunteer organisations struggle to obtain resources for basic operations, which reduces their efficiency and ability to fulfil their mission.

- Acknowledgement and support for organised volunteering: Support from the state and self-governing local communities must continue and be further enhanced. Many volunteer organisations struggle with visibility of their organisations as well as their contributions to society. Recognising volunteer work as a significant factor in attaining social objectives is crucial for their successful operations. To this end, cross-sectoral and inter-ministerial planning of pilot projects, research in the field of volunteering and greater support for organisations providing volunteer programmes (social work centres, healthcare and educational institutions for the development of volunteer programmes, organisations in the youth sector carrying out volunteer programmes and other public institutions) must be promoted.

- Education and training: Volunteers and their mentors should have access to high-quality educational programmes and training to enable them to develop the skills and knowledge necessary for efficient work. In specific fields of volunteer work, supervision must be provided by suitably qualified individuals. Ongoing education and knowledge upgrades are important so that volunteer organisations can respond efficiently to changing social challenges.

- Legislative framework: Improving relevant sectoral legislation affecting the operations of volunteer organisations and volunteering is imperative, including insurance for volunteers and administrative support. The legislative framework must be adapted to the specific needs of volunteering and facilitate organisational operations.

- Awareness raising and promotion: Based on studies and research it is necessary to enhance public awareness of the importance of volunteering and its positive impact on society. Recognising the value of volunteering is crucial for increasing participation in and support for volunteer activities.

- Fundamental policies for the development of volunteering

The fundamental policies for developing volunteering in Slovenia include:

- Financial stability: Ensuring stable financing of volunteering based on multi-annual calls for proposals with integral and European funds is vital. Financial stability is also of utmost importance for long-term planning and the successful mission implementation. Various sources of financing must be developed for stable operations.

- Supportive environment: Providing a supportive environment facilitates access to the necessary work resources (e.g. ICT equipment) and supports the efficient operation of volunteer organisations.

- Systemic harmonisation of health insurance for volunteers: Examining and amending the legislation relating to insurance for volunteers against work-related injuries and occupational diseases.

- Cross-sectoral cooperation: Promoting collaboration between different sectors, such as the public (healthcare, education, culture, social protection, etc.), the business and the non-governmental sectors, is essential for effectively utilising volunteer resources. Such cooperation is crucial for tackling social challenges comprehensive.

- Promotion and awareness-raising: Promotional measures should be developed to raise awareness of the importance of volunteering in society with the aim of increasing visibility and value of volunteer work.

- Strengthening the capacities of organisations: To implement their mission, it is essential to boost the capacities of volunteer organisations by providing a supportive environment. This includes education, training, mentoring and competence development to ensure a high-quality volunteering experience. Strengthening the capacities of volunteer organisations will result in the better management and implementation of volunteer programmes.

- Strategic development objectives of volunteer organisations/volunteering

The strategic objectives for the period up to 2030 are as follows:

- A stable and sustainable environment for volunteer organisations: This objective aims to create a stable environment for the operations of volunteer organisations, enabling long-term planning and the implementation of their programmes and activities. This includes promoting diversified financing models and providing support for the stable operation of the organisations.

- Strengthening of operational and management capacities: The objective is to enhance the capacities of volunteer organisations by providing supportive environment for the efficient implementation of their programmes and ensuring quality mentoring and training for volunteers. Strengthening capacities will enable better management and implementation of the organisation’s mission.

- Increasing the number of volunteers and providing a quality volunteering experience: The objective is to improve the operations of volunteer organisations through training, mentoring, and efficient management. Emphasis will be placed on promoting volunteering that encourages equal opportunities for all, irrespective of gender, age or other circumstances, and on volunteering in social assistance programmes, which greatly contributes to supporting their users.

- Greater visibility and importance of volunteering: The objective is to enhance the reputation and visibility of volunteering in society, particularly through increased media coverage and greater presence in educational and public institutions. Key measures include conferring state awards and recognition, the active participation of volunteer organisations in the Council of the Government of the Republic of Slovenia for the Promotion of the Development of Volunteering and Volunteer and Non-Governmental Organisations, the implementation of national research into volunteering, and an analysis of the types of volunteer work in social protection. Another key element is ensuring the public is informed about volunteering and including volunteering content in the education system.

- Volunteer programmes that address social issues such as the loneliness among young people, an ageing population, migration, poor-quality leisure time, climate change and similar, will promote various types of volunteering, such as family volunteering, e-volunteering, corporate volunteering. These programmes will also enhance cooperation between volunteer organisations and public institutions and support volunteering as a means of preventing mental health issues.  Another important highlight is reinforcing the capacities of NGOs to increase social resilience.

- The role of the state and self-governing local communities in achieving development objectives

The state, self-governing local communities and other relevant stakeholders play an important role in achieving the development objectives of volunteering and volunteer organisations:

- The state must strive to provide stable financing for the development of organised volunteering, adjust legislation to reflect the specific needs of volunteering and provide a supportive environment for volunteer organisations and volunteering. This includes systemic financing, a suitable regulatory framework for organised volunteering, and the promotion of social responsibility. In its social role, the state must also play a key part in establishing the conditions for successful volunteering.

- Self-governing local communities must encourage local initiatives and volunteer programmes, provide support to local volunteer organisations, and establish partnerships with different local stakeholders. Local communities play a key role in promoting volunteering at a local level and ensuring support for local organisations.

- The business sector and economic associations must promote social responsibility in companies and encourage their participation in volunteering programmes. This can include financial support, such as donations and sponsorship of volunteer campaigns as well as encouraging employees to participate in volunteer activities (corporate volunteering). Companies’ contribution to the development of volunteering in the form of financial resources, infrastructure and expertise are indispensable.

- Educational institutions should strive to incorporate volunteering into their programmes and promote collaboration between educational institutions and volunteer organisations. They play a key role in forming the values and skills that contribute to young people becoming active citizens.

- Main fields of volunteering development

The main fields of development include:

- Ongoing, diversified and transparent financing: It is necessary to promote long-term financing models that provide volunteer organisations with multi-annual financial resources, including public calls for proposals, private donations and European funds. Stable financing is crucial for long-term operations and the successful implementation of programmes.

- Legal and administrative support: Legislation governing the insurance of volunteers must be addressed, and executive acts governing the field of volunteer work and its evaluation must be updated. Legal and administrative support contributes to the efficient day-to-day running of volunteer organisations and to the provision of a safe environment for volunteers.

- Education and training: A supportive environment must be financed systemically to provide educational programmes for volunteers and mentors in different fields of volunteering, develop structured educational programmes and ensure ongoing training and support. High-quality education and training are fundamental building blocks in the development of competent and motivated volunteers.

- Promotion of volunteering: Activities to raise awareness about volunteering may include media presence and promotion within the framework of different educational programmes. Promotion of volunteering must be ongoing and aimed at various target groups to enhance the visibility, understanding and the social value of volunteer work.

- Cross-sectoral cooperation: To address social challenges, it is necessary to promote collaboration between various sectors, including public administration, businesses, volunteer organisations and organisations that provide volunteer programmes. Such cooperation is crucial for resolving social challenges and increasing the impact of volunteering.

- Development and evaluation of new volunteering programmes that respond to current social challenges.

- Action plan for the implementation of the Volunteering Development Strategy

| Strategic goal | Measure | Activity | Implementation period | Responsible entity/ participants | Source of funds | Criteria for assessing the attainment of objectives | Target value | Amount of funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| a) Stable and sustainable environment for volunteer organisations | Strengthening multi-annual public calls for proposals with recommendations to ministries and municipalities | Encourage the use of multi-annual public calls for proposals to facilitate long-term project/programme planning and implementation and provide advice and recommendations to ministries and municipalities | 2025–2030 | Ministry of Public Administration |  | Recommendations to ministries Recommendations to municipalities | 1 recommendation/year 1 recommendation/year | Activity does not require additional financial resources |
|  | Review and amendment of legislation on volunteer insurance | Systemic harmonisation of health insurance for volunteers for work-related injuries and occupational diseases | 2026–2027 | Ministry of Health, Ministry of Labour, Family, Social Affairs and Equal Opportunities, Ministry of Public Administration in cooperation with the horizontal volunteer network |  | Amended legislation | 1 legislative change/implementation period | Activity does not require additional financial resources |
|  | Review and amendment of the Rules on Areas of Volunteer Work and the Register | Review and amendments to the Rules on Areas of Volunteer Work and the Register to realistically evaluate volunteer work | 2025–2026 | Ministry of Public Administration in cooperation with the horizontal volunteer network |  | Amended Rules on Areas of Volunteer Work and the Register | 1 legislative change/implementation period | Activity does not require additional financial resources |
| b) Strengthening of operational and management capacities | Support for volunteer organisations through the horizontal volunteer network and strengthening regional hubs in the field of volunteer activities | Public calls for proposals for supportive environment entities are intended for horizontal networks at the national level and regional hubs (12) that act as support organisations for the development, strengthening and professionalisation of NGOs and volunteering, including strengthening the development of smaller NGOs | 2025–2030 | Ministry of Public Administration | Fund for the Development of NGOs BI 180151 | Implemented public calls for proposals – fully functioning horizontal volunteer network and regional hubs strengthened in the field of volunteer activities | 1 public call for proposals/implementation period | EUR 10,000,000 |
|  | Operational support for volunteer organisations and organisations with volunteer programmes | Implementation of activities to support volunteering at the national and regional level (training, advocacy, information, etc.) | 2025–2030 | Horizontal volunteer network and regional hubs |  | Number of funded supportive environment entities | 13 funded entities/implementation period | Activity does not require additional financial resources |
| c) Increasing the number of volunteers and ensuring a quality volunteering experience | Supervision for mentors as an eligible cost in public calls for proposals | Inclusion of mentors’ supervisions as eligible costs in public calls for proposals where this is justified | 2025–2030 | Ministry of Public Administration and other competent ministries |  | Number of public calls for proposals that include supervision as an eligible cost (including as part of a lump sum/flat rate) | 10 public calls for proposals/implementation period | Activity does not require additional financial resources |
|  | Professionalisation of volunteer mentors and coordinators | Co-financing of sustainable jobs for volunteer mentors and coordinators as well as training courses that will contribute to the development and professionalisation of NGOs and volunteering in Slovenia | 2026–2030 | Ministry of Public Administration | Fund for the Development of NGOs BI 180151 | Number of public calls for proposals | 2 public calls for proposals/implementation period | EUR 15,000,000 |
|  | Promotion of volunteering among older employees | Producing a brochure containing information on good practices and the benefits of volunteering | 2027 | Horizontal volunteer network, Ministry of Public Administration |  | Designed and disseminated brochure | 1 designed and disseminated brochure/implementation period | Activity does not require additional financial resources |
|  | Promotion of volunteer work in the field of equal opportunities of women and men | Recognition of volunteer work in projects on gender equality | 2030 | Ministry of Labour, Family, Social Affairs and Equal Opportunities | Integral part of the budget of the Ministry of Labour, Family, Social Affairs and Equal Opportunities BI 130089 | Number of volunteers participating in the gender equality projects and programmes | 5 projects annually with the option to evaluate and include volunteer work hours in the financial plans of projects | Activity does not require additional financial resources |
|  | Promotion of volunteering in social care – social assistance programmes | Enhancement and promotion of volunteer work with public calls for proposals for co-financing of social protection programmes | 2030 | Ministry of Labour, Family, Social Affairs and Equal Opportunities |  | Increased number of completed volunteer hours in social assistance programmes | Increase by 20 per cent as per the base year 2024/implementation period | Activity does not require additional financial resources |
|  | Training for social protection providers | Promotion of volunteer work and an increase in the number of volunteers in social protection | 2026–2030 | Ministry of Labour, Family, Social Affairs and Equal Opportunities, Social Chamber of Slovenia | Integral part of the budget of the Ministry of Labour, Family, Social Affairs and Equal Opportunities BI 4077 | Number of training sessions | 1 training until 2030/implementation period | EUR 4,000 |
| d) Greater visibility and importance of volunteering | Enhancing the reputation and significance of volunteering in society and increasing the media presence of volunteering | Promoting the social impact of volunteering in the media Increasing media presence on International Volunteer Day and volunteer awards ceremonies, etc. | 2025–2030 | Ministry of Public Administration, Government Communication Office |  | Number of posts on volunteering (state awards and recognitions, International Volunteer Day, etc.) | 10 posts in the media/implementation period | Activity does not require additional financial resources |
|  | Conferring of state awards and recognitions for volunteer work | Conferring of awards and recognitions for volunteer work (public call, administrative support to the Committee of the Republic of Slovenia for national recognition awards in volunteering) | 2025–2030 | Ministry of Public Administration, Government Communication Office | Integral part of the budget of the Ministry of Public Administration BI 153395 | Ensuring the annual state award and recognition ceremony for volunteers | 5 state awards and recognitions for volunteers/implementation period | EUR 9,000/year |
|  | Participation of volunteer organisations in the Council of the Government of the Republic of Slovenia for the Promotion of the Development of Volunteering and Volunteer and NGOs | Regular structured dialogue of volunteer organisations in the Council | 2025–2030 | Ministry of Public Administration, members of the Council | Integral part of the budget of the Ministry of Public Administration BI 153395 | Number of Council meetings Number of initiatives by volunteer organisations discussed | 2 meetings of the Council/year 2 initiatives discussed/year | EUR 500/meeting |
|  | Conducting national research on volunteering | Implementation of national research on the impact of volunteering to obtain a comprehensive insight of the scope, economic value, demographic and geographic trends, and social impact of volunteering in Slovenia | 2026–2030 | Ministry of Public Administration, Slovenian Research and Innovation Agency | Integral part of the budget of the Ministry of Public Administration BI 153372 | Research implementation Presentation at the Council Publication of research findings at GOV.SI. | 1 research/implementation period | EUR 50,000 |
|  | Analysis of types of volunteer work in the field of social protection | Analysis of the types of volunteer work in the field of social protection with an emphasis on the inclusion of socially excluded groups in volunteer work | 2026 | Ministry of Labour, Family, Social Affairs and Equal Opportunities, Social Protection Institute of the Republic of Slovenia | Integral part of the budget of the Ministry of Labour, Family, Social Affairs and Equal Opportunities BI 1279 | Research implemented | 1 research/implementation period | EUR 50,000 |
|  | Strengthening the quality and development of volunteering in cultural heritage protection, library and archive services | Development of: – volunteer programmes in cultural heritage protection, library and archive services for target groups (young and older people, the unemployed, volunteering as a measure of social activation) – a system for recording volunteer hours and work - consideration of volunteer work in public calls and calls for proposals | 2026–2030 | Ministry of Culture |  | Drafted programmes Drafted and implemented recording system Incorporation of volunteer work in public calls and calls for proposals | 3 programmes/implementation period 1 recording system/implementation period 3 public calls or calls for proposals with incorporated volunteer work/implementation period | Activity does not require additional financial resources |
|  | Raising public awareness of the volunteer work indicators | Developing and promoting of the Strategy and joint annual reports on volunteering | 2025–2030 | Ministry of Public Administration |  | Number of posts in the media Online publication of annual reports | 2 posts in the media/year 1 online publication/year | Activity does not require additional financial resources |
|  | Promotion of volunteering and content of active, responsible and solidarity-oriented individuals in schools and other institutions in education and training | Minister responsible for education highlights the importance of volunteering and the characteristics of active, responsible and solidarity-oriented individual at the beginning of the school year; minister also attends national volunteering events | 2025–2030 | Ministry of Education |  | Number of events (report on activities) | 3 events/year | Activity does not require additional financial resources |
|  | Adequate support in raising awareness of the values of volunteering in mentoring volunteers, as well as in promoting qualities of an active, responsible and solidarity-oriented members of society in public educational institutions | Organisation of annual consultations for mentors and coordinators of volunteering as well as for formation of active, responsible and solidarity-oriented members of society in kindergartens, primary and secondary schools, secondary school dormitories, and institutions for children with special needs | 2025–2030 | Ministry of Education, National Education Institute of the Republic of Slovenia, horizontal volunteer network |  | Number of consultations (report on activities) | 3 consultation sessions/year | Activity does not require additional financial resources |
| e) Volunteer programmes for addressing social challenges | Promoting volunteering to address social challenges and encouraging various forms of volunteering (family volunteering, e-volunteering, corporate volunteering, etc.) | Public calls for proposals to promote volunteering, increase the accessibility and flexibility of volunteering for different target groups with the aim of strengthening social resilience, promoting sector integration and enabling greater sustainability of volunteering | 2027–2030 | Ministry of Public Administration | Fund for the Development of NGOs BI 180151 | Number of public calls for proposals for co-financing of projects/programmes of volunteer organisations | 1 public call for proposals/implementation period | EUR 980,000 |
|  | Promotion of mentoring in cultural heritage protection, library and archive services | Developing volunteering programmes for cultural heritage protection, library and archive services for target groups (young and older people, unemployed, volunteering as a measure of social activation) Organisation of training for mentors | 2026–2030 | Ministry of Culture |  | Programmes prepared Implementation of training | 3 programmes/implementation period 1 training/implementation period | Activity does not require additional financial resources |
|  | Promoting cooperation between volunteer organisations and public institutions | Promotion and presentation of best collaboration practices between volunteer organisations and public institutions | 2025–2030 | Ministry of Public Administration in cooperation with the horizontal volunteer network and regional hubs |  | Number of presented best practices | 1 presentation/year | Activity does not require additional financial resources |
|  | Promoting various types of volunteering as a preventive or protective mental health factor for various target groups | Public calls for proposals for the promotion of various types of volunteering as a preventive mental health factor for different target groups | 2025–2029 | Ministry of Health, National Institute of Public Health | Integral part of the budget of the Ministry of Health BI 221091 European cohesion funds BI 230642 BI 230643 BI 230644 BI 230645 | Number of public calls for proposals for the co-financing of the projects/programmes of volunteer organisations | 2 public calls for proposals/implementation period | EUR 300,000 |
|  | Strengthening NGOs/volunteer organisations to increase the societal resilience | Training of NGOs/volunteer organisations and different volunteer groups | 2025–2030 | Ministry of Defence | Ministry of Defence – dedicated funds BI 4791 – Fire Fund | Number of training sessions or exercises in individual fields | 20–30 training sessions or exercises/year | EUR 1,000,000/year |
|  | Inclusion of volunteers under the Act on Temporary Measures to Improve Personnel and Working Conditions and Capacity of Providers of Social Protection and Long-Term Care Services (ZZUKDPSS) | Public call for the provision of funds for the involvement of volunteers with providers of social protection and long-term care services | 2025–2026 | Ministry of Solidarity-Based Future | Integral budget of the Ministry of Solidarity-Based Future BI 230395 Inclusion of volunteers under the ZZUKDPSS | Number of public calls | 2 public calls | EUR 345,000 |

9. Conclusion

The new five-year Volunteering Development Strategy until 2030 is designed to ensure a stable and sustainable environment in which volunteer organisations can operate and volunteering can develop. To realise the proposed measures, the Republic of Slovenia will create a stable and sustainable environment for volunteer organisations, enhance their operational and management capacities and increase the number of volunteers as well as improve their work conditions. The Strategy will also promote diversity and equal inclusion in volunteering, encourage lifelong volunteering for social development and develop volunteer programmes to address social challenges. These measures will contribute to a higher quality of life and social solidarity in Slovenia.

As volunteering forms the basis of social integration and active citizenship, it is crucial that all stakeholders – the government, self-governing local communities, businesses and educational institutions – participate in the implementation of this Strategy. By working together, we can create a more inclusive, sustainable and prosperous future for volunteering that will set an example for other countries to follow. We believe that, through joint efforts and dedication, we will achieve the set objectives and subsequently create a better future for all.

10.   References

- A statute for European cross-border associations and non-profit organizations – Potential benefits in the current situation (2021). https://www.europarl.europa.eu/RegData/etudes/STUD/2021/693439/IPOL_STU(2021)693439_EN.pdf

- Anheier, H. K. (2009). What kind of Nonprofit sector, What kind of Society?, American Behavioural Scientist, 52, pp. 1082–1094.

- CEV – Centre for European Volunteering. (2011). P.A.V.E. – Policy Agenda for Volunteering in Europe.
https://www.europeanvolunteercentre.org/pave

- CEV – Centre for European Volunteering. (2020). Blueprint for European Volunteering 2030 (BEV2030). https://www.europeanvolunteercentre.org/bev2030

- CEV – Centre for European Volunteering. (2023). European Volunteering Infrastructure in 2022.
https://www.europeanvolunteercentre.org

- Targeted research project, Potencial NVO v Sloveniji za naslavljanje potreb lokalnih skupnosti (The potential of non-governmental organisations in Slovenia to address the needs of local communities). (University of Ljubljana, 2023).
https://www.gov.si/novice/2024-05-23-raziskava-potencial-nevladnih-organizacij-za-naslavljanje-potreb-lokalnih-skupnosti

- European Commission. (2023). Proposal for a Directive on European Cross-Border Associations (ECBAs).
https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A52023PC0516

- European Parliament. (2022). Resolution on cross-border associations and non-profit organisations.
https://www.europarl.europa.eu/doceo/document/TA-9-2022-0041_EN.html

- International Labour Organization (ILO). (2011). Manual on the Measurement of Volunteer Work.
https://www.ilo.org/wcmsp5/groups/public/---dgreports/---stat/documents/publication/wcms_162119.pdf

- Johns Hopkins University. (2003). Global Civil Society: An Overview.
https://ccss.jhu.edu/wp-content/uploads/downloads/2011/10/Global-Civil-Society-2003.pdf

- Lang, S. (2010). NGOs, Civil Society, and the Public Sphere. Cambridge University Press.
https://www.cambridge.org/core/books/ngos-civil-society-and-the-public-sphere/27E494BE3A3318B5BDE4571990CF1259

- Lewis, D. (2020). Non-Governmental Organizations and Development (2nd edition). Routledge.
https://www.routledge.com/Non-Governmental-Organizations-and-Development/Lewis/p/book/9780367334083

- OECD. (2018). The Role of Civil Society in Strengthening Democratic Governance.
https://www.oecd.org/governance/the-role-of-civil-society-in-strengthening-democratic-governance.pdf

- Ordinance on the Strategy for the Development of Non-Governmental Organisations and Volunteering until 2023, Official Gazette of the Republic of Slovenia [Uradni list RS], No. 37/18.
https://www.uradni-list.si/glasilo-uradni-list-rs/vsebina/2018-01-1271

- Rakar, T. et al. Final report of the research project, The potential of non-governmental organisations to address the needs of local communities.
https://www.gov.si/novice/2024-05-23-raziskava-potencial-nevladnih-organizacij-za-naslavljanje-potreb-lokalnih-skupnosti

- Recommendation CM/Rec(2007)14 of the Committee of Ministers to member states on the legal status of non-governmental organisations in Europe of 10 October 2007
https://search.coe.int/cm/Pages/result_details.aspx?ObjectID=09000016805d534d

- Rojc Štremfelj, L., Žnidaršič, J., Marič, M. (2020). Government-Funded Sustainable Development and Professionalisation of NGOs, Sustainability, 12(18):7363.
https://doi.org/10.3390/su12187363

- Salamon, L. M., & Anheier, H. K. (1996). The International Classification of Nonprofit Organizations: ICNPO.
https://ccss.jhu.edu/publications-findings/?did=126

- Centre for Information, Cooperation and Development of Non-Governmental Organisations – CNVOS website.
https://www.cnvos.si/nvo-sektor-dejstva-stevilke/stevilo-nvo/

- European Economic and Social Committee (EESC).
https://www.eesc.europa.eu/en/agenda/our-events/events/european-statute-associations-and-ngos

- Slovenian Development Strategy 2030. (2017).
https://www.gov.si/assets/ministrstva/MKRR/Strategija-razvoja-Slovenije-2030/Strategija_razvoja_Slovenije_2030.pdf

- Council of Europe. (2018). International Standards Relating to Reporting and Disclosure Requirements for Non-Governmental Organizations.
https://www.coe.int/en/web/ingo/expert-council

- Council of Europe. (2021). The Legal Space for Non-Governmental Organisations in Europe. 
https://www.coe.int/en/web/ingo/expert-council

- Würmli, S., and Jenny, B. (2024). Maximizing Impact with Results-Based Financing: 9 Learnings from a New Report.
https://www.linkedin.com/pulse/maximizing-impact-results-based-financing-9-learnings-sandro-würmli

- Act on Non-Governmental Organisations (ZNOrg). Official Gazette of the Republic of Slovenia [Uradni list RS], No. 21/18.
http://pisrs.si/Pis.web/pregledPredpisa?id=ZAKO7430

Official Gazette of the Republic of Slovenia [Uradni list RS], Nos. 10/11, 16/11 – corr. and 82/15.

Official Gazette of the Republic of Slovenia [Uradni list RS], No. 37.

Lewis, D. (2020), Non-Governmental Organizations and Development (Routledge Perspectives on Development), 2nd edition, p. 32.

Article 2 of the ZProst.

OECD (2024), Unleashing the Potential of Volunteering for Local Development, OECD Publishing, Paris. Available at: https://www.oecd.org/cfe/unleashing-the-potential-of-volunteering.pdf.

Centre for European Volunteering (CEV). (2011). P.A.V.E. – Policy Agenda for Volunteering in Europe: Working towards a true legacy for EYV 2011. https://www.europeanvolunteercentre.org/_files/ugd/3ec99c_38c7cd0ec9b4490fbd96230430959e35.pdf

CEV – Centre for European Volunteering (CEV). (2020). Blueprint for European Volunteering 2030 (BEV2030). Brussels: CEV. https://www.europeanvolunteercentre.org/bev2030

Cronin, K. and Perold, H. (2006). Volunteering and Social Activism: Pathways for Participation in Human Development. The International Journal of Volunteer Administration, vol. XXVI, No. 1.

Government of the Republic of Slovenia. (2017). The Slovenian Development Strategy 2030. Ministry of Economic Development and Technology. Available at: https://www.gov.si/assets/ministrstva/MKRR/Strategija-razvoja-Slovenije-2030/Strategija_razvoja_Slovenije_2030.pdf

The 2024 joint report on volunteering in the Republic of Slovenia is available at https://www.gov.si/teme/prostovoljstvo/.

UN Volunteers. (2020). Volunteering and COVID-19: The Moment to Reshape Volunteering for the 2030 Agenda.

International Federation of Red Cross and Red Crescent Societies (2022). Volunteering for a stronger, more resilient society.

Centre for European Volunteering (CEV) (2011). P.A.V.E. – Policy Agenda for Volunteering in Europe: Working towards a true legacy for EYV 2011. https://www.europeanvolunteercentre.org/_files/ugd/3ec99c_38c7cd0ec9b4490fbd96230430959e35.pdf

The supportive environment entities in accordance with Article 24 of the ZNOrg:

- A horizontal network is a non-governmental organisation which at the national level brings together non-governmental organisations from different thematic areas of operation and performs the activities of informing, consultancy, education, research, advocacy, networking, promotion and support for the benefit of all non-governmental organisations at the national level.

- A regional hub is a non-governmental organisation which, at the level of a development region as laid down in the act governing balanced regional development or at the level of several municipalities representing a complete spatial entity, brings together non-governmental organisations from different thematic areas of operation and performs the activities of informing, consultancy, education, research, advocacy, networking, promotion and support for the benefit of all non-governmental organisations at the level of its operation.

- A thematic network is a non-governmental organisation which, at the national level, at the level of a development region as laid down in the act governing balanced regional development, or at the level of several municipalities representing a complete spatial entity, brings together non-governmental organisations from the same thematic area and performs the activities of informing, consultancy, education, research, advocacy, networking, promotion and support for the benefit of all non-governmental organisations from the same thematic area at the level of its operation.

Resources are anticipated under the measure “Support to volunteer organisations through the horizontal volunteer network and strengthening of regional hubs in the field of volunteer activities”.

The target value of tenders for NGOs will be EUR 120,000 in 2030.